## Slide 1: Moving CaterFlow from Sanity to MongoDB
Options, considerations and pricing
4 October 2026
Notes: Opening: this deck covers why CaterFlow should move its live data from Sanity to MongoDB, what the quoted SZL 20,000 buys, and the hosting choices, including a server in the office. Source documents: the migration plan and quote (15 September 2026), the retention report (22 September 2026) and the accuracy audit (4 October 2026).

## Slide 2: Executive summary
Moving live data to MongoDB removes a ceiling that new features push toward, and ends the two-database split behind the stock and report errors.
31,059
live Sanity documents when production was blocked
24,784
documents to migrate and verify
20,000
SZL fixed fee, 96–139 estimated hours
3–4
weeks of full-time build, plus a rollback window
Hosting is separate
Atlas, a rented server or an office server all work, because the app needs only a connection string.
Office has conditions
Off-site backup, a private link instead of an open port, and a UPS.
The Sanity bill ends
The subscription is cancelled once the migration is verified.
Notes: The decision in one page. Production was blocked by Sanity's document quota at about 31,059 live documents. The migration touches about 24,784 documents and is quoted as a fixed SZL 20,000 over 96 to 139 estimated hours. Hosting is not part of the quote. Timeline: the work is now full-time, so about 3 to 4 weeks of build at 40 hours a week (estimate; the quote assumed 4 to 6 months after hours), plus a rollback window. The quote's fixed fee is unchanged here; whether the discounted rate still applies to full-time work is a decision for G-Solutions².

## Slide 3: The quota is already binding
The deletion step checked the archive date instead of the business date, so the 60-day cleanup barely ran.
Chart: Documents deletable under the 60-day policy
| Dispatch logs | Purchase orders | Goods receipts | Inventory counts | File attachments | Stock adjustments
Deletable before the fix | 1 | 576 | 0 | 1 | 0 | 8
Deletable after the fix | 4307 | 2241 | 2219 | 167 | 3009 | 0
586 → 11,943
documents deletable, before and after the fix
Not yet deployed
Take a backup first: the next cleanup will try to delete about 11,900 documents in one pass.
Notes: Source: retention findings report CATERFLOW-RETENTION-2026-09-22-R2. Before the fix only 586 documents passed the deletion gate; after it, 11,943. The fix is in code and tested but not deployed. The report itself says the fix is necessary but not sufficient.

## Slide 4: New data outgrows the cleanup
Archive-and-delete can only shrink the live count to one 60-day window of new documents. It can never go below that.
A floor, not a cure
Only documents older than 60 days are removed.
Everything newer stays live, so the live count tracks the rate of new records.
Never deleted
694 master records: 601 stock items, 34 users, 18 bins, 17 suppliers, 16 categories, 8 sites.
Drafts, in-progress records and purchase orders awaiting receipts.
New features add
Any feature that stores new records in Sanity adds to it.
The reports plan proposes period-close and opening-balance records.
No document growth rate is recorded in the repository, so this is argued from structure. Measuring weekly growth by type would put a date on it.
Notes: This is the structural argument. After a delete pass, the live count settles near the number of documents created in the last 60 days, plus whatever cannot be deleted yet. Several kinds of document are never deleted. We have not measured growth, so I am not putting a date on it; that is a recommended next step.

## Slide 5: Two stores cause wrong numbers
Documents older than 60 days live only in MongoDB, while most code reads Sanity alone.
Sanity
Last 60 days of documents
MongoDB archive
Everything older than 60 days
Merge, cap and de-duplicate in every query
F-01
A recalculation rebuilds stock from only the last 60 days, understating everything received earlier.
F-02
Archived events are not de-duplicated, so a document in both stores is counted twice.
F-04
Stock as of a date, and history older than 60 days, read Sanity only and come back wrong or empty.
Source: accuracy audit, 4 October 2026. The faulty code was confirmed by reading; F-02's live impact is still to be verified.
Notes: The accuracy audit traces the Reports errors and several stock errors to the two-store design. F-01, F-02 and F-04 are severity S1 or confirmed findings. Each new feature that needs history has to merge the stores again, and each place that forgets produces another wrong number.

## Slide 6: Why MongoDB
It removes the document ceiling and the second store, and the app already speaks to it.
One store, no merge
Live and old documents share collections; history is one query.
No document quota
Limits are disk, memory and throughput, not document count.
Server-side summaries
Aggregation returns a 1 KB summary, not the full history.
Indexed queries
Date, site and bin indexes keep range queries cheap.
Transactions
A receipt and its stock update succeed or fail together.
Already in the app
The native mongodb driver and ETL scripts already exist.
Notes: Mongo is not chosen because it is automatically faster. The gains come from one store, no quota, server-side aggregation with indexes, transactions on a replica set, and the fact that the app already uses the native driver for archive history. Transactions need a replica set.

## Slide 7: What changes after the move
Most differences are gains, but two jobs move into the application.
Area | Today (Sanity plus archive) | After (MongoDB)
Data stores | Two: Sanity and the MongoDB archive | One
Document limit | Sanity quota, blocked at about 31,059 | Bound by disk and throughput
History queries | Merge, cap and de-duplicate | One query
Report summaries | Full history downloaded | 1 KB server-side aggregate
Retention machinery | Required to stay under quota | Mostly removable
Reference integrity | Enforced by Sanity schemas | Moves into the app (Mongoose recommended)
Admin editing | Sanity Studio | A minimal internal admin screen
Not automatic: the 194 GROQ queries must be rewritten with sensible indexes, or some will be slower.
Notes: Be candid about the two jobs that move into the app: reference integrity, because Mongo does not enforce references the way Sanity does, and admin editing, because Studio goes away. Query speed also depends on indexes being designed with the rewrite.

## Slide 8: What has to move
Sanity is used for login, every operational record and file storage, so the migration touches almost the whole app.
64
files import Sanity
54
API routes
~194
GROQ queries to rewrite
24
document types
24,784
documents to migrate
Authentication
Login, password reset and verification codes move to a MongoDB users collection.
References
Each Sanity reference becomes an ObjectId link or an embedded subdocument.
File storage
A replacement provider (S3, Cloudinary or UploadThing) takes over from Sanity's CDN.
Admin screen
A minimal internal screen replaces Studio for one-off data corrections.
Notes: Numbers come from the codebase as read in September 2026: 64 files import Sanity, 54 route files, about 194 GROQ blocks and 211 fetch calls, 24 schema types and about 24,784 documents in the latest production export. No evidence the client uses Studio directly, but that needs confirming with them.

## Slide 9: Four phases, one switch at the end
CaterFlow keeps running on Sanity until each phase is verified, which avoids one high-risk cutover.
Phase 1
Foundation
Collection design
Auth rewrite
Migration scripts on staging
Done when: Counts and references match the export
Deposit SZL 10,000 before start
Phase 2
Core operations
Stock, procurement
Purchase orders
Goods receipt
Done when: Each route passes a UI smoke test
SZL 5,000 on completion
Phase 3
Remaining routes
Dispatch, transfers
Adjustments, reports
Admin, file storage
Done when: Regression matrix passes
No payment due
Phase 4
QA and cutover
Full regression
Production migration
Sanity read-only, then retired
Done when: Production counts verified
SZL 5,000 on go-live
Notes: Phasing lets CaterFlow keep running on Sanity throughout most of the project and cut over only once each phase is verified. Payment milestones: SZL 10,000 deposit before work starts, SZL 5,000 on completion of Phase 2, SZL 5,000 on go-live after Phase 4 sign-off. The regression matrix is re-run at the end of each phase.

## Slide 10: Where the SZL 20,000 goes
The API rewrite is 40% of the fee: 54 routes and about 194 queries, rewritten one by one.
Chart: Fixed fee by workstream (SZL)
| API route rewrite | Testing and QA | Schema design | Data migration | Admin screen | File storage | Auth rewrite | Cutover
Fee (SZL) | 8000 | 2500 | 2000 | 2000 | 1900 | 1400 | 1200 | 1000
SZL 20,000
fixed fee, 96–139 estimated hours
SZL 170 / hour
discounted project rate for the size of the engagement
Notes: Fees by workstream sum to SZL 20,000. Hours by workstream: API rewrite 40 to 55, QA 12 to 18, schema design 10 to 14, data migration 10 to 14, admin screen 8 to 14, file storage 6 to 10, auth 6 to 8, cutover 4 to 6, totalling 96 to 139. The standard rate is not stated in the quote, so I am not quoting a discount percentage.

## Slide 11: How the fixed fee was set
At SZL 170 an hour, 96–139 hours spans SZL 16,320 to SZL 23,630. The fixed fee sits near the middle.
SZL 20,000 fixed fee (about 118 hours)
SZL 16,320
96 hours at SZL 170
SZL 23,630
139 hours at SZL 170
≈118 hours
what SZL 20,000 buys at SZL 170 an hour
SZL 144–208
effective hourly rate across the 139 to 96 hour range
12–17 min
per GROQ query inside the 40–55 hour API rewrite
Our risk
if the work overruns, G-Solutions² absorbs it, not the client
Notes: Arithmetic: 96 x 170 = 16,320; 139 x 170 = 23,630; 20,000 / 170 = about 117.6 hours; 20,000 / 139 = about 144 per hour; 20,000 / 96 = about 208 per hour. API rewrite 40 to 55 hours over about 194 queries is 12 to 17 minutes each. One caution: the migration plan's phase estimates add up to 92 to 129 hours, while the quote's workstreams add up to 96 to 139. Reconcile them before the client compares the documents.

## Slide 12: Payment and what is not included
The fee is billed in three milestones and covers development time only.
SZL 10,000
50% deposit before work starts
SZL 5,000
25% on completion of Phase 2
SZL 5,000
25% on go-live after Phase 4 sign-off
Not in the fee
Database hosting
Atlas is billed directly by MongoDB. This deck shows no Atlas prices.
File storage
The provider (S3, Cloudinary or UploadThing) bills directly.
Self-hosting setup
Provisioning, hardening, tunnel, backups and monitoring need their own line.
What it offsets
The Sanity subscription ends once cutover is verified. Its cost is not recorded yet.
Notes: Work starts only once the quote is signed and the SZL 10,000 deposit has been received. The quote assumes MongoDB Atlas for hosting, billed directly by MongoDB with no markup. If the client self-hosts, provisioning, hardening, tunnelling, backup automation and monitoring are extra scope. Payback against the Sanity subscription cannot be calculated until we know what the client pays Sanity today.

## Slide 13: Four ways to host MongoDB
The app needs only a connection string, so the host can change later without code changes.
Option | Who operates it | Cost shape | Main risk | Best when
Atlas (managed) | MongoDB: patching, replica set, backups on paid tiers | Monthly tier, rising with storage and throughput | Recurring cost grows with data | No one can maintain a server
Rented server (VPS) | Client or G-Solutions²: patches, backups, monitoring | Flat monthly fee plus operating time | You own operations; one node is a single point of failure | A technical person is available
Office server | Client or G-Solutions², plus the office's power and network | Hardware, UPS and internet plus operating time | An outage stops the whole business | Data must stay on-premises and power and internet are reliable
Hybrid: office plus off-site replica | As office, plus the off-site part | Office costs plus a small off-site server | More parts to monitor | You want on-premises control and real disaster recovery
Self-hosted options need a replica set, ideally three data-bearing members, for failover and transactions. No prices are shown because none are recorded in the quote or repository.
Notes: MongoDB Community Server is free to self-host. The real differences are who carries operations and availability risk. A single node is acceptable only for development. I have deliberately not quoted hosting prices because none are recorded in the repository.

## Slide 14: Reaching an office database
Vercel's functions connect from changing public IPs, so they cannot reach an office network without help.
Vercel app
Tunnel or private link
Office MongoDB
Preferred
Tunnel or private link
Cloudflare Tunnel or Tailscale. No router ports are opened. It adds a dependency and some latency, and must be tested with Vercel's functions.
Avoid
Port-forward
Needs a static public IP and a hardened server. An exposed database is a common cause of data loss.
Alternative
App moves in-house
The database never leaves the LAN, but Vercel's convenience is lost and the office hosts the web app too.
Notes: The app is described as a Next.js app on Vercel. How Vercel's functions connect through a tunnel needs testing before we commit. The port-forward option is listed only so we can explicitly rule it out.

## Slide 15: What the building adds
Today the app is as available as Sanity and Vercel. On an office server, the office's power and internet become CaterFlow's uptime.
Power
A UPS with runtime for a clean shutdown, and an inverter or generator for longer cuts.
Internet
Remote users, such as site managers on mobile, depend on the office uplink.
Backups
A nightly dump copied off-site, with restores tested. A backup in the same building is not a backup.
Security
Authentication and TLS, a private interface, a firewall, least-privilege users, patching.
Hardware
Mirrored SSDs, disk and health alerts, and a three-member replica set.
Ownership
A named person for patching, monitoring and recovery. Not yet identified.
Notes: The backup point matters most. The repository already has scripts/export_mongo.js and BACKUP_SAFETY_GUIDE.md, which are a starting point, but neither covers an off-site copy. Two members in the office plus one off-site protects against losing the whole building. Nobody is named as owner of operations in the plan, quote or repository.

## Slide 16: Six conditions before cutover
Go ahead with an office server only if every one of these is met.
An off-site backup runs automatically and a restore has been tested
The app reaches the database through a tunnel or private link, with no open database port
A UPS protects the server and the office has reliable internet
A named person is responsible for patching, monitoring and recovery
A replica set has at least one off-site member, or the client accepts single-node risk in writing
Authentication and TLS are enabled and tested
If one is missing
Stay on Atlas until it is met.
A database outage would stop dispatch, receipts and counts for the whole business.
Notes: These six conditions are the gate for office hosting. Because the app only needs a connection string, the system can move from Atlas to an office server later, once the conditions are met, without code changes.

## Slide 17: Risks to manage
The biggest near-term risk is the gap: migration takes about 3–4 weeks of full-time work, and the quota is binding today.
Risk | Why it matters | Mitigation
Quota block continues | Blocked at about 31,059 live documents; the deletion fix is not deployed | Backup, deploy the fix, run one archive pass and one delete pass, check the counts
Quota and tier unknown | The assumed 50,000-document tier was contradicted | Confirm plan, limit and price on the Sanity billing page
Reference integrity | MongoDB does not enforce references like Sanity | Mongoose validation; verify every reference on staging
Slower queries | GROQ joins become $lookup pipelines that need indexes | Index by date, site and bin; test heavy routes on real-sized data
Images and Studio | Image transforms and Studio use are unconfirmed | Check each attachment; ask the client directly
Cutover | Writes during the switch could be lost or duplicated | Agree downtime and rollback windows; keep Sanity read-only
Also open: the plan's phase hours (92–129) differ from the quote's workstreams (96–139), and retention is 90 days locally against a 60-day code default.
Notes: The quota block is the urgent item: the migration takes weeks and Sanity is binding now, so the retention fix needs to be deployed in the meantime, after a backup. Also confirm ARCHIVE_DAYS_THRESHOLD in production.

## Slide 18: Recommendation and next steps
Proceed at the quoted SZL 20,000, and choose the production host after Phase 1, once real data volumes are known.
1
Unblock Sanity now. Back up, deploy the retention fix, run one archive and one delete pass, confirm the quota.
2
Sign the quote and pay the SZL 10,000 deposit so Phase 1 can start.
3
Stage on a managed or rented MongoDB during Phases 1 and 2, with no dependence on the office.
4
Choose the production host after Phase 1. Atlas by default; an office server only if all six conditions are met.
5
If self-hosting, add a costed line for setup, hardening, backups and monitoring.
6
Reconcile the hours and put the open questions to the client before Phase 1 starts.
7
Measure before and after: weekly document growth by type, and one endpoint's latency.
Notes: Step one is urgent and independent of the migration decision. Step three keeps the build away from office infrastructure while the schema and routes are being proven. The quote itself already recommends reviewing real usage after Phase 1 before committing to a paid plan.

## Slide 19: What we need from the client
Six answers settle the hosting choice and unblock Phase 1.
1
Does any attachment depend on Sanity's image CDN transforms?
2
Does any person or tool use Sanity Studio directly?
3
What downtime and rollback window is acceptable for cutover?
4
Which hosting option is preferred, and who would maintain it?
5
How reliable are the office's power and internet?
6
What does the Sanity plan cost today?
Notes: These are the open questions from the migration plan plus the hosting questions raised since. The answers on hosting, power and internet decide whether an office server is viable.